## Summary
Matrix Topic	Device Management Library and Firmware
Project	ET SOC 1
Owner(s)	Mentor

Revision History
Matrix Rev.	Change Description	Person of Change	Date of Change
1.0	Created draft template	Shankar Jayaratnam	02-05-20
1.1	Added Device Management Tess	Etsam Anjum	03-01-21
2	Reorganization of tests	Mahad Saleem	11-28-22

## Instructions
Test Matrix Instructions: Version 1.0 02/04/2020

Format
Summary page should be completed for all test matrices. Should be kept up to date for revision info.
All other sheets should have the format shown in the "TestPlan" example sheet (an exception would be the rollup page the spc team uses for counting tasks to do).
User may create as many extra Feature sheets as needed to organize data. Key is to ORGANIZE your info
Copy this sheet before adding your info so that you have a blank template handy for when you need to create a new sheet
Do NOT change the names of any of the existing columns in the Test Matrix (the post processing scripts look for those exact names)
Users can add additional columns to the spreadsheet for their own use. New columns are best added at the right after the comments section
For specifics on what content should go in each column, roll your cursor over the top row of the column and a popup note will provide info on what should be added

Content
Matrix should be organized to follow the Specification. that it is testing
The doc. column in the matrix (Column A) should be filled out per section or item so that the test or feature info in the matrix is linked to the document that describes it
There should be a line item in the matrix for all relevant or interesting features/items/cases in the Spec
Even items in the Spec that are not explicitly tested in your plan should be called out to address who owns testing to ensure no gaps

Background
Users will enter plan data in this Matrix
Matrix will be used along with SW/HW Specification for reviews for completeness
Scripts will be used to pull info from this matrix
A web page will track expected data supplied by this matrix vs. what has been written and released and is in use in regressions
Statistics will be available on work completed vs work left to do.

## Functional
Terminology
Positive Testing: Tests that validate functionality of a given interface in response to expected input args, in supported usage model
Negative Testing: Tests that validate functionality of a given interface in response to unexpected/ill-formatted input args, outside the scope of supported usage model
Labels: Labels are useful. ctest -L <label> executes all tests with label
PCIE: Tests is for etsoc1-pcie-driver
SYSEMU: Tests is for SysEMU
OPS: Tests involving operations on ops node
MGMT: Tests involving operations on mgmt node
FUNCTIONAL: Test case simply validates some functionality
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
UNIT: Tests only part of system, e.g: one ioctl
SYSTEM: Tests multiple functionalities involved in a flow

Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

System Functional Tests: System level testing of functionality provided by DM library. Includes both positive and negative testing.
Note: All tests listed in the plan shall be implemented and executed for PCIe driver environments.
Test Labels	File Name	Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>	Reference to Documentation	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
		DM Sync Services (Functional Testing)
FUNCTIONAL	FunctionalTestDevMgmtApiAssetTrackingCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleManufactureName		Gets the manufacture name and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModulePartNumber		Gets the part number and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.setAndGetModulePartNumber		Gets the default part number, then sets the test part number and gets the part number and compares them. Reverts back to default values.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleSerialNumber		Gets the serial number and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getASICChipRevision		Gets the chip revision and compares it with the value maintained locally. Test is passed if the value matches.		Done
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModulePCIENumPortsMaxSpeed		Gets the chip revision and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleMemorySizeMB		Gets the chip revision and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleRevision		Gets the module revision and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleFormFactor		Gets the module form factor and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleMemoryVendorPartNumber		Gets the memory vendor part number and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiAssetTrackingCmds.getModuleMemoryType		Gets the module memory type and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
FUNCTIONAL	FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModulePowerState		Sets the power state and reads it back. The two states are compared and test is passed if they match.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.setAndGetModuleStaticTDPLevel		Sets the TDP level and reads it back. The two levels are compared and test is passed if they match.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.setAndGetModuleTemperatureThreshold		Sets the temperature threshold and reads it back. The two values are compared and test is passed if they match.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModuleResidencyThrottleState		Gets the module time spend in the throttling state. Test is passed if the DM request return status is a success.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModuleUptime		Gets the module up time since the restart. Test is passed if the return status is a success.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModulePower		Gets the module power Test is passed if the return status is a success. Better check would be to make sure return power stays within extreme limits. Limits will be shared by the ET.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModuleVoltage		Gets the module voltage.Test is passed if the return status is a success. Better check would be to make sure return voltage stays within extreme limits. Limits will be shared by the ET.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.setAndGetModuleVoltage		Gets the default module voltage. Sets new voltages and get them back and expect that values set are within 5% of set voltage values. Revert back to default voltage.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModuleCurrentTemperature		Gets the module temperature The test is passed if the DM request return status is a success. Just to catch insane value, a range check can be imposed e.g the max cannot exceed 20% above the upper threshold limit.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.getModuleResidencyPowerState		Gets the module residency power state.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleActivePowerManagement		Gets the module active power.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiThermalAndPowerMonitoringCmds.setThrottlePowerStatus		Sets the module throttle power status		Done	Yes
FUNCTIONAL	FunctionalTestDevMgmtApiHistoricalExtremeValCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiHistoricalExtremeValCmds.getModuleMaxTemperature		Gets the historical extreme value of temperature. The test is passed if the return status of DM command is success. The test can be further enhanced by reading the values with some delay and make sure that latest value is >= to previous one.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiHistoricalExtremeValCmds.getModuleMaxMemoryErrors		Gets the historical extreme value of memory errors. The test is passed if the return status of DM command is success. The test can be further enhanced by reading the values with some delay and make sure that latest value is >= to previous one.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiHistoricalExtremeValCmds.getModuleMaxDDRBW		Gets the historical extreme value of DDR BW The test is passed if the return status of DM command is success. The test can be further validated by reading the values with some delay and make sure that latest value is >= to previous one.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiHistoricalExtremeValCmds.getModuleMaxThrottleTime		Gets the historical extreme value of time spent in throttle state. The test is passed if the return status of DM command is success. The test can be further enhanced by reading the values with some delay and make sure that latest value is >= to previous one.		Done	Yes
FUNCTIONAL	FunctionalTestDevMgmtApiErrorControlCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiErrorControlCmds.setAndGetDDRECCThresholdCount		Sets the DDR Correctable errors threshold and reads it back. The two values are compared and test is passed if they match.		Done	Yes					Get threshold service is unsupported
		deviceManagement:FunctionalTestDevMgmtApiErrorControlCmds.setAndGetSRAMECCThresholdCount		Sets the SRAM Correctable errors threshold and reads it back. The two values are compared and test is passed if they match.		Done	Yes					Get threshold service is unsupported
		deviceManagement:FunctionalTestDevMgmtApiErrorControlCmds.setAndGetPCIEECCThresholdCount		Sets the SRAM Correctable errors threshold and reads it back. The two values are compared and test is passed if they match.		Done	Yes					Get threshold service is unsupported
FUNCTIONAL	FunctionalTestDevMgmtApiLinkMgmtCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.getPCIEECCUECCCount		Gets the PCIE correctable/un-correctable error count The test is passed if the return status of DM command is success. Just to catch insane value a range check can be added as well.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.getDDRECCUECCCount		Gets the DDR correctable/un-correctable error count The test is passed if the return status of DM command is success. Just to catch insane value, a range check can be added as well		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.getSRAMECCUECCCount		Gets the SRAM correctable/un-correctable error count The test is passed if the return status of DM command is success. Just to catch insane value a range check can be added as well.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.getDDRBWCounter		Gets the DDR BW Counters. The test is passed if the return status of DM command is success. Just to catch insane value, a range check can be imposed.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.setPCIELinkSpeed		Sets the PCIE link speed and reads it back. The two values are compared and test is passed if they match.		Done	Yes					Get PCIE link speed service is unsupported
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.setPCIELaneWidth		Sets the PCIE Lane Width reads it back. The two values are compared and test is passed if they match.		Done	Yes					Get PCIE linke widrh service is unsupported
		deviceManagement:FunctionalTestDevMgmtApiLinkMgmtCmds.setPCIERetrainPhy		Retrains PCIe phy. The test is passed if the return status of DM command is success. Needs further qualification.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getASICFrequencies		Gets ASIC frequencies. The test is passed if the return status of DM command is success.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getDRAMBW		Duplicates 5.4		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilization		Gets DRAM capacity utilization The test is passed if the return status of DM command is success.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilization		Gets ASIC per core utilization. The test is passed if the return status of DM command is success.<Needs further qualification>		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getASICUtilization		Gets complete ASIC utilization. The test is passed if the return status of DM command is success.<Needs further qualification>		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getASICStalls		Gets complete ASIC stalls. The test is passed if the return status of DM command is success.<Needs further qualification>		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiPerfMgmtCmds.getASICLatency		Gets the ASIC latency. The test is passed if success response is received		Done
FUNCTIONAL	FunctionalTestDevMgmtApiFirmwareMgmtCmds.cpp	deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.getMMErrorCount		Gets the MM error count. The test is passed if success response is received		Done
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.getFWBootstatus		Gets device firmware boot status. The test is passed if success response is received		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.getModuleFWRevision		Gets device firmware revision. The test is passed if success response is received and firmware version matches pre defined value		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.setSpRootCertificate		Set the root certificate of service processor.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.updateFirmwareImage		Update firmware image		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.setAndGetModuleFrequency		Sets the list of test frequency pairs {minion, noc} and read them back to validate if frequencies are set properly.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.resetSOCSingleDevice		Complete SOC reset, re-initialize the single device after reset and validate that it is functional.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.resetSOCMultiDevice		Complete SOC reset, re-initialize the multi device after reset and validate that it is functional.		Done	Yes
		deviceManagement:FunctionalTestDevMgmtApiFirmwareMgmtCmds.resetSOCNoOpsNode		SOC reset should be success even if the OPS node is not available in the system. Remove OPS node and do SOC reset.		Plan	Yes
FUNCTIONAL	fwupdate.sh.in	deviceManagement:fwupdate.verifyPartitionHeader		Verify partition header of input image is valid		Plan	Yes			1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.	1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
		deviceManagement:fwupdate.verifyImageSize		Verify size of input image is valid (image size is less than scratch region size)		Plan	Yes			1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.	1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
		deviceManagement:fwupdate.verifyRequiredRegionsPresence		Verify input image has all the required regions		Plan	Yes			1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.	1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
		deviceManagement:fwupdate.verifyRegionsChecksum		Verify region info checksum for all regions		Plan	Yes			1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.	1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
		deviceManagement:fwupdate.verifyRegionsOffsetAndSize		Verify offset and size for all regions		Plan	Yes			1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.	1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
		deviceManagement:fwupdate.updateFirmwareOnPartition1		Verify device is able to boot successfully from partition 1 after firmware update		Plan	Yes			1. Hot reset support is required. / 2. New Mgmt device API for host to get active partition number from device.	1. Hot reset support is required. / 2. New Mgmt device API for host to get active partition number from device.		To be run only on Silicon
		deviceManagement:fwupdate.updateFirmwareOnPartition0		Verify device is able to boot successfully from partition 0 after firmware update		Plan	Yes			1. Hot reset support is required. / 2. New Mgmt device API for host to get active partition number from device.	1. Hot reset support is required. / 2. New Mgmt device API for host to get active partition number from device.		To be run only on Silicon

## Integration
Terminology
Positive Testing: Tests that validate functionality of a given interface in response to expected input args, in supported usage model
Negative Testing: Tests that validate functionality of a given interface in response to unexpected/ill-formatted input args, outside the scope of supported usage model
Labels: Labels are useful. ctest -L <label> executes all tests with label
PCIE: Tests is for etsoc1-pcie-driver
SYSEMU: Tests is for SysEMU
OPS: Tests involving operations on ops node
MGMT: Tests involving operations on mgmt node
FUNCTIONAL: Test case simply validates some functionality
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
UNIT: Tests only part of system, e.g: one ioctl
SYSTEM: Tests multiple functionalities involved in a flow

Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

System Functional Tests: System level testing of functionality provided by DM library. Includes both positive and negative testing.
Note: All tests listed in the plan shall be implemented and executed for PCIe driver environments.
Test Labels	File Name	Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>	Reference to Documentation	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
		DM Sync Services (Functional Testing)
		System/Integration Tests		The purpose of this test suite is to make sure that ops and mgmt nodes can be used simultaneously. For mgmt nodes, the tests from 1.1 to 7.1 and 11.x should be executed along with the ops node tests.		Plan
INTEGRATION	IntegrationTestDevMgmtApiCmds.cpp	deviceManagement:IntegrationTestDevMgmtApiCmds.serializeAccessMgmtNode		Creates three threads that requests DM service with different timeouts. The second thread tries to access the mgmt device while it is still in use (locked) by the first thread and therefore immediately returns with error (as it invokes the function with 0 timeout). The thread three invokes the DM service with the timeout value higher than the first thread and so waits for the mgmt device to be released by the first thread. It completes successfully.		Done	Yes
INTEGRATION		deviceManagement:IntegrationTestDevMgmtApiCmds.getDeviceErrorEvents				Done
INTEGRATION		deviceManagement:IntegrationTestDevMgmtApiCmds.setTraceControl		Set the trace control, either trace is directed toward serial or trace buffer.		Done	Yes
INTEGRATION		deviceManagement:IntegrationTestDevMgmtApiCmds.setTraceConfigure		Configure trace for different filter/events and check if DM command returns success.		Done	Yes
INTEGRATION		deviceManagement:IntegrationTestDevMgmtApiCmds.getTraceBuffer		Gets the trace buffer and checks if the required trace is obtained.		Done	Yes
INTEGRATION		deviceManagement:IntegrationTestDevMgmtApiCmds.getMMThreadStateXX		Gets MM state. The test is passed if the return status of DM command is success. Also, the state is validated against valid range (enums)		Plan	Yes

## MDI
Terminology
Positive Testing: Tests that validate functionality of a given interface in response to expected input args, in supported usage model
Negative Testing: Tests that validate functionality of a given interface in response to unexpected/ill-formatted input args, outside the scope of supported usage model
Labels: Labels are useful. ctest -L <label> executes all tests with label
PCIE: Tests is for etsoc1-pcie-driver
SYSEMU: Tests is for SysEMU
OPS: Tests involving operations on ops node
MGMT: Tests involving operations on mgmt node
FUNCTIONAL: Test case simply validates some functionality
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
UNIT: Tests only part of system, e.g: one ioctl
SYSTEM: Tests multiple functionalities involved in a flow
MDI: MDI Debug tests, involving breakpoint, memory read/write and register read/write tests

Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

System Functional Tests: System level testing of functionality provided by DM library. Includes both positive and negative testing.
Note: All tests listed in the plan shall be implemented and executed for PCIe driver environments.
Test Labels	File Name	Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>	Reference to Documentation	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
		MDI Tests
MDI	RunControlApiTestcmds.cpp	deviceManagement:RunControlApiTestcmds.testRunControlCmdsSetandUnsetBreakpoint		Sets and unsets breakpoint using MDI command interface. Test passes by checking the hart status after resume.		Done	Yes
		deviceManagement:RunControlApiTestcmds.testRunControlCmdsGetHartStatus		Gets the hart status and display it, test halts a hart and gets the status. It then resume hart after getting status.		Done	Yes
	StateInspectionApiTestcmds.cpp	deviceManagement:StateInspectionApiTestcmds.readMem_unprivileged		This test reads a memory location in unprivileged region mentioned in mdi debug. Test passes on successful read.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.readMem_privileged		This test reads a memory location in privileged region mentioned in mdi debug. Test passes on access error as the privileged region should not be accessible.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.writeMem_unprivileged		This tests writes a test data in unprivileged memory region. Test passes after reading back the data and successful comparrison with data to write.		Done
		deviceManagement:StateInspectionApiTestcmds.writeMem_privileged		This test try to write a memory location in privileged region mentioned in mdi debug. Test passes on access error as the privileged region should not be accessible.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.readMem_unprivileged		Gets the chip revision and compares it with the value maintained locally. Test is passed if the value matches.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.testStateInspectionReadGPR		This test reads a GPR register and print it’s value.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.testStateInspectionWriteGPR		This test writes test data to GPRs, it restores the data back after testing.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.testStateInspectionReadCSR		This test reads a CSR register and print it’s value.		Done	Yes
		deviceManagement:StateInspectionApiTestcmds.testStateInspectionWriteCSR		This test writes test data to CSRs, it restores the data back after testing.		Done	Yes

## Security
Terminology
Positive Testing: Tests that validate functionality of a given interface in response to expected input args, in supported usage model
Negative Testing: Tests that validate functionality of a given interface in response to unexpected/ill-formatted input args, outside the scope of supported usage model
Labels: Labels are useful. ctest -L <label> executes all tests with label
PCIE: Tests is for etsoc1-pcie-driver
SYSEMU: Tests is for SysEMU
OPS: Tests involving operations on ops node
MGMT: Tests involving operations on mgmt node
FUNCTIONAL: Test case simply validates some functionality
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
UNIT: Tests only part of system, e.g: one ioctl
SYSTEM: Tests multiple functionalities involved in a flow

Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

System Functional Tests: System level testing of functionality provided by DM library. Includes both positive and negative testing.
Note: All tests listed in the plan shall be implemented and executed for PCIe driver environments.
Test Labels	File Name	Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>	Reference to Documentation	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
		DM Sync Services (Security/Negative Testing)		These test cases invoke the DM library APIs using out of range parameters for write requests(set type) and validates that the DM lib catches them and returns the appropriate errors. These tests do not cover extensive argument validation, that is covered in next section. Furthermore, the valid ranges are tested with the above tests 1.1 to 7.1
SECURITY	SecurityTestDevMgmtApiGenericCmds.cpp	deviceManagement:SecurityTestDevMgmtApiGenericCmds.isUnsupportedService		Error is returned if invalid arguments are passed (device node, command code, input buffer, output buffer, host latency and device latency)		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiGenericCmds.testInvalidCmdCode		Error is returned if command type is invalid		Done	Yes
SECURITY	SecurityTestDevMgmtApiAssetTrackingCmds.cpp	deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidInputSize		Error is returned if invalid input size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiAssetTrackingCmds.getModuleManufactureNameInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY	SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.cpp	deviceManagement:SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleActivePowerManagementRange		Check power state API with invalid state. Error is returned by the DM lib when an invalid power state i.e state not defined in the enum POWER_STATE , is set		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleSetTemperatureThresholdRange		Error is returned by the DM lib when a threshold is set which is outside of permissible range. The correct range is to be provided by the ET		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleStaticTDPLevelRange		Error is returned by the DM lib when an invalid static TDP level i.e. level not defined in the enum TDP_LEVEL, is set		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleActivePowerManagementRangeInvalidInputSize		Error is returned if invalid input buffer size is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiThermalAndPowerMonitoringCmds.setModuleActivePowerManagementRangeInvalidInputBuffer		Error is returned if invalid/null pointer to input buffer is passed while service command is of set type.		Done	Yes
SECURITY	SecurityTestDevMgmtApiHistoricalExtremeValCmds.cpp	deviceManagement:SecurityTestDevMgmtApiHistoricalExtremeValCmds.getHistoricalExtremeWithInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiHistoricalExtremeValCmds.getHistoricalExtremeWithInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiHistoricalExtremeValCmds.getHistoricalExtremeWithInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiHistoricalExtremeValCmds.getHistoricalExtremeWithInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiHistoricalExtremeValCmds.getHistoricalExtremeWithInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY	SecurityTestDevMgmtApiErrorControlCmds.cpp	deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidInputBuffer		Error is returned if invalid/null pointer to input buffer is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidInputSize		Error is returned if input buffer size is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setDDRECCCountInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCCountInvalidInputBuffer		Error is returned if invalid/null pointer to input buffer is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidInputSize		Error is returned if input buffer size is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setPCIEECCountInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCCountInvalidInputBuffer		Error is returned if invalid/null pointer to input buffer is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCCountInvalidInputSize		Error is returned if input buffer size is passed while service command is of set type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCountInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCountInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCountInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCountInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiErrorControlCmds.setSRAMECCountInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY	SecurityTestDevMgmtApiLinkMgmtCmds.cpp	deviceManagement:SecurityTestDevMgmtApiLinkMgmtCmds.setPCIELinkSpeedToInvalidLinkSpeed		Error is returned when invalid PCIE link speed is set.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiLinkMgmtCmds.setPCIELaneWidthToInvalidLaneWidth		Error is returned when invalid PCIE lane width is set.		Done	Yes
SECURITY	SecurityTestDevMgmtApiPerfMgmtCmds.cpp	deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICFrequenciesInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICFrequenciesInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICFrequenciesInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICFrequenciesInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICFrequenciesInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMBandwidthInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMBandwidthInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMBandwidthInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMBandwidthInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMBandwidthInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilizationInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilizationInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilizationInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilizationInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getDRAMCapacityUtilizationInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilizationInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilizationInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilizationInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilizationInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICPerCoreDatapathUtilizationInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICUtilizationInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICUtilizationInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICUtilizationInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICUtilizationInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICUtilizationInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICStallsInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICStallsInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICStallsInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICStallsInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICStallsInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICLatencyInvalidOutputSize		Error is returned if invalid output size is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICLatencyInvalidDeviceNode		Error is returned if invalid device node is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICLatencyInvalidHostLatency		Error is returned if invalid/null pointer for host latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICLatencyInvalidDeviceLatency		Error is returned if invalid/null pointer for device latency is passed		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.getASICLatencyInvalidOutputBuffer		Error is returned if invalid/null pointer to output buffer is passed while service command is of get type.		Done	Yes
SECURITY		deviceManagement:SecurityTestDevMgmtApiPerfMgmtCmds.setModulePowerStateRangeInvalidInputBuffer		Error is returned if invalid/null pointer to input buffer is passed while service command is of set type.		Done	Yes
SECURITY	fwupdate.sh.in	deviceManagement:fwupdate.imageWithInvalidPartitionHeaderFields		Verify error is generated if partition header of input image is invalid (header fields are not correct)		Plan	Yes				1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
SECURITY		deviceManagement:fwupdate.imageWithOutOfBoundsSize		Verify error is generated if input image size is greater than scratch region size		Plan	Yes				1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
SECURITY		deviceManagement:fwupdate.imageWithZeroSize		Verify error is generated if input image is of zero size		Plan	Yes				1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash.
SECURITY		deviceManagement:fwupdate.imageWithSizeLessThanPartitionSize		Verify error is generated if input image size is less than partition size		Plan	Yes				1. Firmware update code in SP BL2 needs to be extended to perform verification checks on input update image before writing the image on flash. / 2. Support in device API and it’s handling so that host can also pass image size to device in addition to image.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition1WithCorruptBL1		Verify device is able to boot successfully using valid partition 0 if update image on partition 1 fails in BL1		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition1WithCorruptBL2		Verify device is able to boot successfully using valid partition 0 if update image on partition 1 fails in BL2		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition1WithCorruptMM		Verify device is able to boot successfully using valid partition 0 if update image on partition 1 fails in MM		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition0WithCorruptBL1		Verify device is able to boot successfully using valid partition 1 if update image on partition 0 fails in BL1		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition0WithCorruptBL2		Verify device is able to boot successfully using valid partition 1 if update image on partition 0 fails in BL2		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.
SECURITY		deviceManagement:fwupdate.updateFirmwareOnPartition0WithCorruptMM		Verify device is able to boot successfully using valid partition 1 if update image on partition 0 fails in MM		Plan	Yes				1. Hot reset support is required. / 2. Need support in SP BL1 and SP BL2 to pass on error code, if any to next stage.

## Stress
Terminology
Labels: Labels are useful. ctest -L <label> executes all tests with label
FUNCTIONAL: Test cases which validate the functionality of the feature
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
INTEGRATION: Tests which require integration with other components of sw-platform stack
SECURITY: Tests which verify the negative paths in the system
PERFORMANCE: Tests which are used for performance analysis of the system

Test prefix: firmwareUpdate
Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<TestName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

Note: Unless otherwise mentioned all tests listed in the plan shall be implemented and executed for both sysemu and PCIe driver environments.
Test Labels	File Name	Test Tag: <TestPrefix>:<TestSuiteName>.<TestName>	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
STRESS	fwupdate.sh.in	deviceManagement.fwupdate.10SuccessiveFirmwareUpdates	Verify 10 successive updates can be performed successfully.		Plan					1. Hot-Reset support is required.		To be run only on Silicon
STRESS	StressTestDevMgmtApiFirmwareMgmtCmds.cpp	deviceManagement:StressTestDevMgmtApiFirmwareMgmtCmds.resetSOCSingleDevice	Iterations: 100, Complete SOC reset, re-initialize the single device after reset and validate that it is functional.		Plan
STRESS		deviceManagement:StressTestDevMgmtApiFirmwareMgmtCmds.resetSOCMultiDevice	Iterations: 100, Complete SOC reset, re-initialize the multi device after reset and validate that it is functional.		Plan

## OpsNodeDependent
Terminology
Positive Testing: Tests that validate functionality of a given interface in response to expected input args, in supported usage model
Negative Testing: Tests that validate functionality of a given interface in response to unexpected/ill-formatted input args, outside the scope of supported usage model
Labels: Labels are useful. ctest -L <label> executes all tests with label
PCIE: Tests is for etsoc1-pcie-driver
SYSEMU: Tests is for SysEMU
OPS: Tests involving operations on ops node
MGMT: Tests involving operations on mgmt node
FUNCTIONAL: Test case simply validates some functionality
STRESS: Multiple/longer cycles of test to see if the test functionality remains consistent
UNIT: Tests only part of system, e.g: one ioctl
SYSTEM: Tests multiple functionalities involved in a flow

Guidelines for test creators
Each Test shall be implemented as a G Test with name identified in the test tag
Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>
Each Test Suite shall be implemented as a independent Cpp module with file name same as the test suite name
All test files within a repo will start with same test prefix

System Functional Tests: System level testing of functionality provided by DM library. Includes both positive and negative testing.
Note: All tests listed in the plan shall be implemented and executed for PCIe driver environments.
Test Labels	File Name	Test Tag format: <TestPrefix>:<TestSuiteName>.<testName>	Reference to Documentation	Test Case Description	Reference to Documentation	Status	Host				Blockers	Debug Hooks	Comments
		DM Sync Services (Ops Node Dependent Testing)
OPS_NODE_DEPENDENT	OpsNodeDependentTestDevMgmtApiTraceCmds.cpp	deviceManagement:OpsNodeDependentTestDevMgmtApiTraceCmds.getMMStatsTraceBuffer		Get MM stats buffer
OPS_NODE_DEPENDENT	OpsNodeDependentTestDevMgmtApiFirmwareMgmtCmds.cpp	deviceManagement:OpsNodeDependentTestDevMgmtApiFirmwareMgmtCmds.resetMM		Reset the MM		Done	Yes
		deviceManagement:OpsNodeDependentTestDevMgmtApiFirmwareMgmtCmds.resetMMWithOpsInUse		Tries to reset MM while the Ops Node is in use.		Done	Yes
		deviceManagement:OpsNodeDependentTestDevMgmtApiFirmwareMgmtCmds.resetSOCWithOpsInUse		Tries to reset SOC while the Ops Node is in use.		Plan	Yes

## Event Reporting
Feature	Test Tag	Test Item or Feature Description	Pointer to Doc	Status	Require Host ?			Configuration or Mode	Blockers	Debug Hooks	Comments

NOTE: Dependencies from ET are called out as comments cells in column "Test Item or Feature Description"
Work in Progress

SP BL2 Event Reporting	Functional Validation Of Async Event Reporting from SP										Incremental testing approach will be taken for validating the event reporting. Firstly, simulated events will be generated from the device side and finally the actual hardware events will be used when the driver support is available. The device events are printed to dmesg by the PCIE driver and normally in servers, the dmesg log is monitored periodically and user is notified (email) when an error is encountered. Most likely, FB will use the same procedure. Host side infra support will be needed fully validate the the same scenario . However for internal testing, we can add a DM request in the DM library that will ask the device to trigger error events. The event generator test task on device side will wait for the requests and then generates the events. The request handler task on device side will send the status after the events have been generated and send to host side. After receiving the status, the host test application will read the dmesg output to the buffer and count the errors. If the error count is correct, the test case will be considered pass. To accentuate, other event fields can be validated. Its possible for host to send a request to device for each event type. The test case listed below assumes a separate request. A note about the hardware events testing, even with actual driver support it may be difficult to create the desired conditions to generate the hardware error. We may have to look for error injection registers to mimic the true scenario.
	T.1.1	Generate PCIE Correctable error event		Done
	T.1.2	Generate PCIE Uncorrectable error event		Done
	T.1.2.1	Generate SRAM Correctable error event		Done
	T.1.3	Generate SRAM Uncorrectable error event		Done
	T.1.4	Generate DDR Correctable error event		Done
	T.1.5	Generate DDR Uncorrectable error event		Done
	T.1.5.1	Generate error event for thermal threshold exceeding lower limit		Done
	T.1.5.2	Generate error event for thermal threshold exceeding higher limit		Done
	T.1.5.3	Generate error event for watchdog timeout		Done